## OffPage_Stack_3Month
Month | Strategy | Target Micro-Area or Page | Specific Action | Output / Cadence | SOP Reference
M1 | DAS (Domain Authority Stack) | Bronx OP coord (3584 Jerome Ave / Norwood) | Push DAS campaign at the Bronx pin to support /outpatient/bronx-outpatient (SP-05 rebuild) + Bronx GBP profile | 1 cycle, 5-7 day pacing per Aaron SOP | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M1 | DAS (Domain Authority Stack) | Queens OP coord (90-02 161st St / Jamaica) | Push DAS campaign at the Queens pin to support /outpatient/queens-outpatient (SP-04 rebuild) + Queens GBP profile | 1 cycle, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M1 | GBP Blast | Bronx — Norwood + Fordham + Williamsbridge + Tremont | Bulk geo-tagged pings around the 4 Bronx neighborhood coords surrounding the Bronx OP pin | 1 cycle, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M1 | GBP Blast | Queens — Jamaica + Flushing + Forest Hills + Astoria | Bulk geo-tagged pings around the 4 Queens neighborhood coords surrounding the Queens OP pin | 1 cycle, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M1 | GBP Sniper | Inpatient Carmel pin (defend) | Tight-radius targeted pings around the Inpatient Carmel 75 Seminary Hill Rd coord. Defend posture only — light cadence. | 1 cycle, low-volume | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M1 | AI Article Creator | /outpatient/bronx-outpatient + /outpatient/queens-outpatient + /inpatient/adult-rehabilitation | 25 spun articles M1 batch. NAP + Google Map iframe embedded in each. Each article points at one of the 3 target pages + relevant GBP profile. Mix of Bronx-anchored + Queens-anchored content. | 25 articles published, staggered 1-2/day across M1 | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M1 | Driving Directions (Tier-0 — principal review) | Bronx OP pin (3584 Jerome Ave) | Add Bronx OP to Driving Directions Masterlist program. Off-shore drivers via Dr Fone + rotating Gmail pool. Orlando regression-window flag — light cadence M1, increase M2 if no regression signal. | Cadence per existing program; Tier-0 principal sign-off required before activation | HQDM/A - HQDM SOPs/Off-Page/Driving-Directions-SOP
M1 | Driving Directions (Tier-0 — principal review) | Queens OP pin (90-02 161st St) | Add Queens OP to Driving Directions Masterlist. Same cadence as Bronx. Orlando regression-window flag — light cadence M1. | Cadence per existing program; Tier-0 principal sign-off required | HQDM/A - HQDM SOPs/Off-Page/Driving-Directions-SOP
M1 | GMB pin creation (gated on address verification) | North Bronx / Wakefield gap coord (proposal) | Stand up a 5th GBP listing if AA can provide a verifiable address in the Bronx-Yonkers gap zone (e.g., clinician office, satellite intake). Without real address = TOS violation. Owner Conversation gate. | Proposal only in M1; deploy in M2 if address confirmed | HQDM/A - HQDM SOPs/Off-Page/GMB-Pin-Creation-SOP
M1 | GMB pin creation (gated on address verification) | Central Queens / Forest Hills gap coord (proposal) | Same gating logic — proposal only, deploy if address verified. | Proposal only in M1; deploy in M2 if address confirmed | HQDM/A - HQDM SOPs/Off-Page/GMB-Pin-Creation-SOP
M2 | DAS (Domain Authority Stack) | Bronx OP + new outer-ring coord (Yonkers) | DAS cycle 2 — re-target Bronx OP plus extend to Yonkers (immediate Bronx-northern adjacency) supporting the /outpatient/bronx-outpatient page + new Bronx Cloud Page if shipped. | Cycle 2, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M2 | DAS (Domain Authority Stack) | Queens OP + new outer-ring coord (LIC / Astoria) | DAS cycle 2 — re-target Queens OP plus extend to LIC/Astoria for the Queens-west grid expansion. | Cycle 2, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M2 | RD100 (re-push top-100 Tier-1 from M1) | Bronx + Queens DAS link surface | Re-push the top-100 highest-authority Tier-1 links generated from M1 DAS campaigns through a second amplification cycle. | Single RD100 cycle covering both M1 DAS targets | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M2 | GBP Blast | Bronx neighborhoods + outer-ring (Yonkers + Pelham Bay) | Cycle 2 with 6 coords (4 M1 Bronx + 2 outer-ring extensions). | Cycle 2, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M2 | GBP Blast | Queens neighborhoods + outer-ring (LIC + Sunnyside) | Cycle 2 with 6 coords (4 M1 Queens + 2 outer-ring). | Cycle 2, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M2 | GBP Sniper | Bronx OP tight-radius around 3584 Jerome Ave | Tighter-radius targeted pings around the Bronx pin to convert the 0-coverage state into proximity rank. | Cycle 1 on Bronx pin (first time) | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M2 | GBP Sniper | Queens OP tight-radius around 90-02 161st St | Tighter-radius pings around the Queens pin to push the 12-25% top-3 share higher (currently median rank 5 on alcohol+drug rehab). | Cycle 1 on Queens pin | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M2 | AI Article Creator | /alcohol-rehab-new-york + /detox-new-york + /inpatient/adult-rehabilitation (deep) | 30 spun articles M2 batch. NAP + Map iframe. Supports the upcoming SP-01/SP-02 NY-state pages once they go live + reinforces the SP-03 adult-rehabilitation improvements from M1. | 30 articles published, staggered 1-2/day across M2 | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M2 | NAP image overlay | /outpatient/queens-outpatient (rebuilt M2) | Screen-capture image with NAP + Queens neighborhood keywords baked on, uploaded to WordPress media library, used as hero/inline image on the rebuilt SP-04 page. | 1 NAP overlay image per new page | HQDM/A - HQDM SOPs/Off-Page/NAP-Image-Overlay-SOP
M2 | NAP image overlay | /outpatient/bronx-outpatient (rebuilt M2) | Same — NAP + Bronx keyword overlay used on the rebuilt SP-05 page. | 1 NAP overlay image per new page | HQDM/A - HQDM SOPs/Off-Page/NAP-Image-Overlay-SOP
M2 | Driving Directions (Tier-0) | Bronx + Queens (continued) | Continue M1 DD program. If no regression signal at M1 close, increase cadence at Bronx + Queens pins. | Cadence per existing program | HQDM/A - HQDM SOPs/Off-Page/Driving-Directions-SOP
M3 | DAS (Domain Authority Stack) | Bronx outer ring — Mt Vernon + New Rochelle adjacent | DAS cycle 3 — extends Bronx-north into Westchester adjacency. Supports /outpatient/bronx-outpatient + Bronx Cloud Page. | Cycle 3, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M3 | DAS (Domain Authority Stack) | Queens outer ring — Long Island Forest Hills + Briarwood | DAS cycle 3 — Queens outer-grid extension. | Cycle 3, 5-7 day pacing | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M3 | RD100 (re-push top-100 from M2 DAS) | Bronx + Queens M2 DAS link surface | Re-push the top-100 from M2 DAS through a second amplification cycle. | Single RD100 cycle covering both M2 DAS targets | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M3 | GBP Sniper | Bronx outer-ring — Fordham + Williamsbridge + Norwood | Sniper on each of the 3 outer-ring Bronx neighborhood coords (tighter than GBP Blast radius). | 3 sniper micro-cycles in M3 | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M3 | GBP Sniper | Queens outer-ring — Astoria + LIC + Forest Hills | Sniper on each of the 3 outer-ring Queens neighborhood coords. | 3 sniper micro-cycles in M3 | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M3 | AI Article Creator | Supporting CN-03 + SP-07 (3 new articles + insurance sub-sections) | 30 spun articles M3 batch reinforcing the M3 supporting articles + insurance carrier sub-sections on /admissions. | 30 articles published, staggered across M3 | HQDM/A - HQDM SOPs/Off-Page/SEO-NEO-Master-Execution-SOP
M3 | NAP image overlay | /alcohol-rehab-new-york + /detox-new-york (new M3 pages) | NAP + Hudson Valley / NYC overlay on the new NY-state pages. | 2 NAP overlay images, one per page | HQDM/A - HQDM SOPs/Off-Page/NAP-Image-Overlay-SOP
M3 | NAP image overlay | /inpatient/adult-rehabilitation (improved) | NAP + Carmel + Putnam County overlay on the M1-improved adult-rehab page. | 1 NAP overlay image | HQDM/A - HQDM SOPs/Off-Page/NAP-Image-Overlay-SOP
M3 | Driving Directions (Tier-0) | Bronx + Queens (M3 baseline measurement) | M3 close: measure DD program impact at Bronx + Queens via the Maps SERP re-pull (LG-INF-02). Decide Q3 continue/throttle/pause. | Cadence continued; M3 measurement gates Q3 decision | HQDM/A - HQDM SOPs/Off-Page/Driving-Directions-SOP