## Schema_Deployment
Month | URL | Page Type | Schema To Deploy | Current Schema | Validation | SOP Reference
M3 | /inpatient/adult-rehabilitation | Inpatient hub | LocalBusiness + Service + FAQPage | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /inpatient/detox-program | Inpatient detox | LocalBusiness + Service | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /outpatient/carmel-outpatient | OP location | LocalBusiness + Service | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /outpatient/bronx-outpatient | OP location (rebuilt M2) | LocalBusiness + Service | None — depends on SP-05 rebuild shipping M2 | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /outpatient/queens-outpatient | OP location (rebuilt M2) | LocalBusiness + Service | None — depends on SP-04 rebuild shipping M2 | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /service/medication-assisted-therapy | Service page | Service | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /service/psychiatric-services | Service page | Service | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /service/alumni | Service page | Service | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /service/recovery-coach | Service page | Service | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /service/equine-therapy-program | Service page | Service | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /service/fitness-recreation-program | Service page | Service | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /admissions | Conversion / Intake | WebPage + LocalBusiness + FAQPage | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /alcohol-rehab-new-york | Service page (NEW) | Service + LocalBusiness | None — ships M3 per SP-01 | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M3 | /detox-new-york | Service page (NEW) | Service + LocalBusiness | None — ships M3 per SP-02 | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M1 | /blog/insurance-cover-drug-and-alcohol-rehab | Blog (M1 batch) | FAQPage | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M1 | /blog/how-to-get-insurance-to-pay-for-inpatient-rehab | Blog (M1 batch) | FAQPage | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M1 | /blog/medicare-cover-alcohol-and-drug-rehab | Blog (M1 batch) | FAQPage | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M1 | /blog/aetna-cover-rehab-treatment | Blog (M1 batch) | FAQPage | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M1 | /blog/tricare-cover-alcohol-and-drug-rehab | Blog (M1 batch) | FAQPage | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP
M1 | /inpatient/adult-rehabilitation | Service page (improve M1) | FAQPage (added via SP-03) | None | Rich Results Test | HQDM/A - HQDM SOPs/On-Page/Schema-Deployment-SOP

## Schema_Validation_M3
URL | Schema Deployed (via task) | Validation Status | Notes
/inpatient/adult-rehabilitation | SP-03 (M1 improve) | TBD post-deploy | FAQPage added via SP-03; verify renders
/alcohol-rehab-new-york | SP-01 (M3 build) | TBD post-deploy | Service + LocalBusiness
/detox-new-york | SP-02 (M3 build) | TBD post-deploy | Service + LocalBusiness
/outpatient/bronx-outpatient | SP-05 (M2 rebuild) | TBD post-deploy | LocalBusiness with Bronx NAP
/outpatient/queens-outpatient | SP-04 (M2 rebuild) | TBD post-deploy | LocalBusiness with Queens NAP