## Dominator_M2
Pin | Month | Strategy | Suburb set targeted | MyMaps target count | Support stack (per Aaron 5-7d pacing) | Target page | GBP target | Acceptance | SOP
Schenectady | M2 | HQDM Dominator | Niskayuna · Rotterdam · Scotia · Glenville (border) · Princetown · Duanesburg | 27 MyMaps | Per existing Dominator program — embed stack + GBP Blast cycle linked to MyMaps batch | /outpatient/schenectady/ | Conifer Park Schenectady GBP CID + target keyword 'drug rehab schenectady' | 27 MyMaps live; all linking back to /outpatient/<pin>/ + GBP; cadence logged in HQDM tracker | Off-Page/SEO-NEO-Master-Execution-SOP / Dominator program
Rochester | M2 | HQDM Dominator | Brighton · Henrietta · Greece · Penfield · Webster · Irondequoit | 27 MyMaps | Per existing Dominator program — embed stack + GBP Blast cycle linked to MyMaps batch | /outpatient/rochester/ | Conifer Park Rochester GBP CID + target keyword 'drug rehab rochester' | 27 MyMaps live; all linking back to /outpatient/<pin>/ + GBP; cadence logged in HQDM tracker | Off-Page/SEO-NEO-Master-Execution-SOP / Dominator program
Syracuse | M2 | HQDM Dominator | Liverpool · Clay · North Syracuse · Salina · Cicero · Onondaga County | 27 MyMaps | Per existing Dominator program — embed stack + GBP Blast cycle linked to MyMaps batch | /outpatient/syracuse/ | Conifer Park Syracuse GBP CID + target keyword 'drug rehab syracuse' | 27 MyMaps live; all linking back to /outpatient/<pin>/ + GBP; cadence logged in HQDM tracker | Off-Page/SEO-NEO-Master-Execution-SOP / Dominator program

## Embedinator_M2
Pin | Month | Strategy | Posture | URL targets | Stack count | Acceptance | SOP
Schenectady | M2 | HQDM Embedinator | Offensive | /outpatient/schenectady/ + GBP | 1 stack per pin (3 stacks total) | Stack live, URL-tracking logged | Off-Page/Embedinator-SOP
Rochester | M2 | HQDM Embedinator | Offensive | /outpatient/rochester/ + GBP | 1 stack per pin (3 stacks total) | Stack live, URL-tracking logged | Off-Page/Embedinator-SOP
Syracuse | M2 | HQDM Embedinator | Offensive | /outpatient/syracuse/ + GBP | 1 stack per pin (3 stacks total) | Stack live, URL-tracking logged | Off-Page/Embedinator-SOP
Glenville | M2 | HQDM Embedinator | Defensive | /outpatient/glenville/ (or homepage for Glenville) + GBP | 1 stack per pin | Stack live, URL-tracking logged | Off-Page/Embedinator-SOP
Plattsburgh | M2 | HQDM Embedinator | Defensive | /outpatient/plattsburgh/ (or homepage for Glenville) + GBP | 1 stack per pin | Stack live, URL-tracking logged | Off-Page/Embedinator-SOP
Troy | M2 | HQDM Embedinator | Defensive | /outpatient/troy/ (or homepage for Glenville) + GBP | 1 stack per pin | Stack live, URL-tracking logged | Off-Page/Embedinator-SOP
Glens-Falls | M2 | HQDM Embedinator | Defensive | /outpatient/glens-falls/ (or homepage for Glenville) + GBP | 1 stack per pin | Stack live, URL-tracking logged | Off-Page/Embedinator-SOP

## SEO_NEO_M2
Pin | Month | Strategy | Article count target | Article angles | Image methodology | Target page | GBP target | Cadence | Acceptance | SOP
Schenectady | M2 | SEO NEO AI Article Creator | 25 articles | (1) Suboxone clinic Schenectady NY (2) MAT walk-in Niskayuna NY (3) Outpatient detox Rotterdam NY (4) Family addiction support Schenectady (5) Same-day MAT Scotia NY — 25 articles total per Aaron methodology | ExifTool image processing + iframe loops + authority-entity injection per Aaron Gruenke SOP | /outpatient/schenectady/ | Conifer Park Schenectady GBP | Aaron 5-7 day pacing | 25 articles deployed; each carries NAP + Map iframe; pointing live | Off-Page/SEO-NEO-Master-Execution-SOP
Rochester | M2 | SEO NEO AI Article Creator | 25 articles | (1) Outpatient rehab Rochester NY (2) Sliding fee addiction treatment Monroe County (3) Suboxone clinic Henrietta NY (4) Dual diagnosis Brighton NY (5) Affordable addiction treatment Greece NY — 25 articles | ExifTool image processing + iframe loops + authority-entity injection per Aaron Gruenke SOP | /outpatient/rochester/ | Conifer Park Rochester GBP | Aaron 5-7 day pacing | 25 articles deployed; each carries NAP + Map iframe; pointing live | Off-Page/SEO-NEO-Master-Execution-SOP
Syracuse | M2 | SEO NEO AI Article Creator | 25 articles | (1) Outpatient rehab Syracuse NY (2) MAT clinic Liverpool NY (3) Drug rehab Clay NY (4) Addiction treatment Onondaga County (5) Suboxone North Syracuse — 25 articles | ExifTool image processing + iframe loops + authority-entity injection per Aaron Gruenke SOP | /outpatient/syracuse/ | Conifer Park Syracuse GBP | Aaron 5-7 day pacing | 25 articles deployed; each carries NAP + Map iframe; pointing live | Off-Page/SEO-NEO-Master-Execution-SOP

## Cloud_Page_M2
Pin | Month | Strategy | Stack (Google Sites + bunny.net/Dropbox) | Title-tag geo-spoof target | Target page | GBP target | Acceptance | SOP
Schenectady | M2 | HQDM Cloud Page | 1 Google Sites + bunny.net or Dropbox supporting stack | Schenectady NY + Niskayuna NY | /outpatient/schenectady/ | Conifer Park Schenectady GBP | Cloud Page live; staging sheet entry logged; title-tag geo-spoof verified | Off-Page/Cloud-Page-SOP
Rochester | M2 | HQDM Cloud Page | 1 Google Sites + bunny.net or Dropbox supporting stack | Rochester NY + Monroe County | /outpatient/rochester/ | Conifer Park Rochester GBP | Cloud Page live; staging sheet entry logged; title-tag geo-spoof verified | Off-Page/Cloud-Page-SOP
Syracuse | M2 | HQDM Cloud Page | 1 Google Sites + bunny.net or Dropbox supporting stack | Liverpool NY + Syracuse NY | /outpatient/syracuse/ | Conifer Park Syracuse GBP | Cloud Page live; staging sheet entry logged; title-tag geo-spoof verified | Off-Page/Cloud-Page-SOP

## Driving_Directions_M2_M3
Pin | Month | Strategy | Origin coords (catchment center) | Destination (GBP coord) | Cadence | Acceptance | SOP
Schenectady | M2 | Driving Directions program | Niskayuna · Rotterdam · Scotia · Glenville-border | Conifer Park Schenectady GBP pin | Monthly cycle per existing program | Origin → destination batch logged in Driving Directions tracker | Off-Page/Driving-Directions-SOP
Schenectady | M3 | Driving Directions program (reinforcement) | Niskayuna · Rotterdam · Scotia · Glenville-border | Conifer Park Schenectady GBP pin | Monthly cycle | Repeat cycle logged | Off-Page/Driving-Directions-SOP
Rochester | M2 | Driving Directions program | Brighton · Henrietta · Greece · Penfield | Conifer Park Rochester GBP pin | Monthly cycle per existing program | Origin → destination batch logged in Driving Directions tracker | Off-Page/Driving-Directions-SOP
Rochester | M3 | Driving Directions program (reinforcement) | Brighton · Henrietta · Greece · Penfield | Conifer Park Rochester GBP pin | Monthly cycle | Repeat cycle logged | Off-Page/Driving-Directions-SOP
Syracuse | M2 | Driving Directions program | Clay · North Syracuse · Salina · Cicero | Conifer Park Syracuse GBP pin | Monthly cycle per existing program | Origin → destination batch logged in Driving Directions tracker | Off-Page/Driving-Directions-SOP
Syracuse | M3 | Driving Directions program (reinforcement) | Clay · North Syracuse · Salina · Cicero | Conifer Park Syracuse GBP pin | Monthly cycle | Repeat cycle logged | Off-Page/Driving-Directions-SOP

## Coverage_Matrix
Pin | GBP access | LD scan | Photo blitz (GBP) | Posts (GBP) | DAS | Embedinator | Sniper | Blast | AI Articles | Driving Directions | NAP overlay | Cloud Page | Review velocity (intake) | Page rebuild | Posture
Glenville | Yes | ✅ (baseline) | (have 26 — ExifTool only) | ✅ defensive 2/wk | — | ✅ | — | — | — | — | — | — | ✅ M2 | (defended) | DEFENSIVE — already dominating
Troy | Yes | ✅ (baseline) | ✅ M1 (3→25) | ✅ offensive 2/wk | — | ✅ | — | — | — | — | ✅ M2 | — | ✅ M2 | ✅ M2 conditional | OFFENSIVE GBP + on-page
Schenectady | No | ✅ M1 | — | — | ✅ M2 + M3 | ✅ | ✅ M2 + M3 | ✅ M2 + M3 | ✅ M2 + M3 | ✅ M2 + M3 (Tier-0) | ✅ M3 | ✅ M2 | ✅ M2 | ✅ M2 | OFFENSIVE site + off-page · GBP out of scope
Rochester | No | ✅ M1 | — | — | ✅ M2 + M3 | ✅ | ✅ M2 + M3 | ✅ M2 + M3 | ✅ M2 + M3 | ✅ M2 + M3 (Tier-0) | ✅ M3 | ✅ M2 | ✅ M2 | ✅ M3 | OFFENSIVE site + off-page (CRO-focused) · GBP out of scope
Syracuse | No | ✅ M1 | — | — | ✅ M2 + M3 | ✅ | ✅ M2 + M3 | ✅ M2 + M3 | ✅ M2 + M3 | ✅ M2 + M3 (Tier-0) | ✅ M3 | ✅ M2 | ✅ M2 | ✅ M3 | OFFENSIVE site + off-page · GBP out of scope
Glens Falls | No | ✅ M1 | — | — | — | ✅ | — | — | — | — | — | — | ✅ M2 | ✅ M3 | Site-side rebuild only · GBP out of scope
Plattsburgh | No | ✅ M1 | — | — | — | ✅ | — | — | — | — | — | — | ✅ M2 | (defended) | Schema only · GBP out of scope