## Outpatient_Pages_Plan
Slug | City | URL | Execution month | GBP access | GSC 365d (pos / CTR / clicks / imp) | GBP (rating × reviews · photos) | Rebuild scope | Word count target | H1 target | Intro hook | Required sections | Schema additions | Intake form spec | GBP UTM target | Neighborhood catchment | Internal links | Photos (live → target) | Acceptance criteria | Owner ask gates | SOP
troy | Troy | /outpatient/troy (canonical post-SP-01) | M2 | Yes (HQDM-supported) | pos 4.66 / 0.897% CTR / 438c / 48,845 imp | 3.9★ × 27 · 3 photos | Conditional rebuild — gated on SP-01 redirect fix outcome. Most likely scenario: /outpatient/troy was the original page; team built a new page at /outpatient-rehab-troy-ny and redirected the original away. Once SP-01 reverses redirect, audit /outpatient/troy content. If substantive, no rebuild needed — light polish only. If thin, rebuild to template here. | 1,200-1,400 (if rebuild) | Outpatient Rehab in Troy, NY — Addiction Treatment Center | Troy-anchored intro (Rensselaer County, transit, distance to Glenville inpatient for step-up LOC) | Hero · Services · About Troy facility · Address + map · Insurance · Inline intake form · FAQ · Reviews · Areas served | MedicalClinic + Place schema with Troy NAP (post-LG-TR-01); Service schema per modality | Inline form with intake CTA above the fold + duplicate after services | ?utm_source=gmb&utm_medium=click&utm_campaign=gmb_listing_troy | Rensselaer · Watervliet · Cohoes · Lansingburgh · Wynantskill · East Greenbush · Albany | From /outpatient hub + Troy area suburbs + /inpatient (step-up referral) | 3 → 25 (M1 photo blitz LG-TR-06) | Per SP-02 conditional audit: (a) light-polish path → schema added + internal links reinforced; or (b) rebuild path → page live with intake form. Either way: LD weekly scans confirm 'outpatient rehab near me' top-3 floor ≥35 cells (per §1b) + recovery toward ≥40 by M3. | Owner Ask #4 — Troy address verification 2431 vs 2435; Owner Ask #6 — Troy photo content | On-Page/Page-Refresh-SOP
schenectady | Schenectady | /outpatient/schenectady/ | M2 | No (GBP out of scope; site-side rebuild only) | pos 5.91 / 1.066% CTR / 401c / 37,630 imp | 2.7★ × 10 · 9 photos | Full rebuild — weakest non-HQDM pin by rating; New Choices (4.2★ × 28) beats at Map Pack #1. Suboxone/MAT is the clinical anchor (Schenectady ranks #2 on suboxone Map Pack already). On-page rebuild is HQDM-deliverable even without GBP access. | 1,200-1,400 | Outpatient Opioid Treatment & Addiction Recovery in Schenectady, NY | Schenectady-anchored intro — Schenectady County, walking distance to Ellis Hospital, suboxone/MAT same-day access emphasized | Hero · Suboxone/MAT (primary clinical anchor — lead) · Services · About facility · Address + map · Insurance · Inline intake form · FAQ · Reviews · Areas served | MedicalClinic + Place schema with Schenectady NAP + Service schema for MAT/Suboxone | Inline form with intake CTA + 'walk-in welcome' for MAT same-day access | (GBP out of scope — UTM repoint deferred) | Niskayuna · Rotterdam · Scotia · Glenville · Princetown · Duanesburg | From /outpatient hub + /services/medication-assisted-treatment (post un-geo-lock) + suburb pages | 9 photos (no blitz — GBP out of scope) | Page live; intake form lives; LD weekly scan shows rank improvement on 'drug rehab schenectady' + Map Pack top-3 within Schenectady centroid | — | On-Page/Service-Page-Build-SOP
glens-falls | Glens Falls | /outpatient/glens-falls/ | M3 | No (GBP out of scope; site-side rebuild only) | pos 10.04 / 1.627% CTR / 255c / 15,672 imp | 3.9★ × 25 · 3 photos · GBP title typo 'Glen Falls' | Page rebuild — best CTR on the site, lowest impressions ceiling. Resolve HTML-encoding artifacts ('&quot;'). On-page rebuild HQDM-deliverable. | 1,200-1,400 | Outpatient Addiction Treatment in Glens Falls, NY | Glens Falls-anchored intro — Warren County / Adirondack region access, distance to Plattsburgh for context | Hero · Services · About facility · Address + map · Insurance · Inline intake form · FAQ · Reviews · Areas served | MedicalClinic + Place schema with Glens Falls NAP | Inline form with intake CTA | (GBP out of scope) | Queensbury · South Glens Falls · Lake George · Hudson Falls · Warrensburg | From /outpatient hub + nearby suburb pages | 3 photos (no blitz — GBP out of scope) | Page live; intake form lives; HTML-encoding artifacts cleaned; LD scans show rank improvement | — | On-Page/Service-Page-Build-SOP
syracuse | Syracuse / Liverpool | /outpatient/syracuse/ | M3 | No (GBP out of scope; site-side rebuild only) | pos 11.75 / 0.922% CTR / 354c / 38,385 imp | 3.4★ × 27 · 6 photos · GBP title 'Liverpool' / site 'Syracuse' | Page rebuild — weakest position. Resolve geographic mismatch on-page (Liverpool physical / Syracuse market). | 1,200-1,400 | Outpatient Addiction Treatment Serving Syracuse, NY (Liverpool location) | Liverpool-physical / Syracuse-market intro — explicit clarification | Hero · Services · About facility · Address + map · Insurance · Inline intake form · FAQ · Reviews · Areas served | MedicalClinic + Place schema with Liverpool NAP; alternateName for Syracuse market | Inline form with intake CTA | (GBP out of scope) | Liverpool · Clay · North Syracuse · Salina · Cicero · Onondaga County | From /outpatient hub + nearby suburb pages | 6 photos (no blitz — GBP out of scope) | Page live with geographic disambiguation; intake form lives; LD scans confirm rank improvement | — | On-Page/Service-Page-Build-SOP
rochester | Rochester | /outpatient/rochester/ | M3 | No (GBP out of scope; site-side rebuild only) | pos 9.36 / 0.819% CTR / 422c / 51,508 imp | 2.7★ × 36 · 5 photos | Page rebuild — HIGHEST IMPRESSIONS on the site (51K/yr) + worst CTR (0.819%) + worst rating drag. CN-03 M1 brief drives architecture. On-page rebuild HQDM-deliverable. | 1,400-1,600 (deepest content — CRO lift) | Outpatient Addiction Treatment Clinic in Rochester, NY | Rochester-anchored intro — Monroe County, public transit, sliding-fee acknowledgment per rating-gap context (Owner Ask #5) | Hero · Insurance + sliding fee (lead) · Services · About facility · Address + map · Inline intake form · FAQ · Reviews · Areas served | MedicalClinic + Place schema with Rochester NAP | Inline form with intake CTA above fold + sticky CTA bar (mobile) | (GBP out of scope) | Brighton · Henrietta · Greece · Penfield · Webster · Irondequoit · Monroe County | From /outpatient hub + nearby suburb pages + /admissions | 5 photos (no blitz — GBP out of scope) | Page live with CRO-focused architecture; intake form lives; M3 measures CTR delta vs M1 baseline (0.819%) | Owner Ask #5 — sliding-fee program details | On-Page/Page-Refresh-SOP + CN-03_Rochester_CRO_Brief.md
plattsburgh | Plattsburgh | /outpatient/plattsburgh/ | — | No (GBP out of scope; defended posture only) | pos 6.96 / 1.079% CTR / 318c / 29,481 imp | 4.2★ × 16 · null photos · null description | DO NOT REBUILD — 4.2★ highest-rating GBP + middling page CTR. Real gap is GBP profile depth (null photos + null description) but GBP is out of scope. Light schema add only. | current (no rebuild) | current title (preserve) | Plattsburgh-anchored intro (current copy preserve) | Hero · Services · About facility · Address + map · Insurance · Intake form · FAQ · Reviews | Add page-level MedicalClinic schema (currently inherits global @graph) | Inline intake form (current — preserve or add) | (GBP out of scope) | Clinton County · Champlain · Peru · West Plattsburgh | From /outpatient hub + Plattsburgh-area suburbs | null photos (no blitz — GBP out of scope) | Schema added on the canonical page; LD scans confirm rank hold at top-3 on 'drug rehab plattsburgh' + 'opioid treatment plattsburgh' | — | On-Page/Page-Refresh-SOP

## Page_Benchmarks
Pin | URL | GSC pos | GSC CTR% | GSC clicks 365d | GSC imp 365d | GBP rating × reviews | GBP photos | GBP access | Q2 posture
Troy | /outpatient/troy | 4.66 | 0.897% | 438 | 48,845 | 3.9★ × 27 | 3 | Yes | IN SCOPE — M2 rebuild conditional + GBP work full
Schenectady | /outpatient/schenectady | 5.91 | 1.066% | 401 | 37,630 | 2.7★ × 10 | 9 | No | Site-side: M2 rebuild + off-page offensive · GBP: out of scope
Plattsburgh | /outpatient/plattsburgh | 6.96 | 1.079% | 318 | 29,481 | 4.2★ × 16 | null | No | Site-side: schema only · GBP: out of scope
Rochester | /outpatient/rochester | 9.36 | 0.819% | 422 | 51,508 | 2.7★ × 36 | 5 | No | Site-side: M3 rebuild + off-page offensive (CRO-focused) · GBP: out of scope
Glens Falls | /outpatient/glens-falls | 10.04 | 1.627% | 255 | 15,672 | 3.9★ × 25 | 3 | No | Site-side: M3 rebuild · GBP: out of scope
Syracuse | /outpatient/syracuse | 11.75 | 0.922% | 354 | 38,385 | 3.4★ × 27 | 6 | No | Site-side: M3 rebuild + off-page offensive · GBP: out of scope