## Trust_Signals_Tracker
Badge / Trust signal | Current status (site grep) | Lookup URL | Required action | Owner side or HQDM-actionable | Target status by M3 | Notes | SOP / Owner Ask reference
OASAS Operating Certificate #10018 | PRESENT (homepage JSON-LD + about-us) | https://oasas.ny.gov/ | Verify still active; add badge to footer + admissions page | HQDM-actionable | Badge visible on footer + admissions + inpatient | Inpatient rehabilitation license; confirmed | On-Page/Trust-Signal-Deployment-SOP
Joint Commission accreditation | ABSENT (no mention anywhere on site) | https://www.qualitycheck.org/ | Confirm status with client; if accredited, deploy badge; if not, owner ask whether pursuing | Owner-side (Owner Ask #3) | Status documented; badge deployed if accredited | Mountainside/Hazelden/AAC all carry — competitive gap | Owner Ask #3
CARF certification | ABSENT (no mention) | https://carf.org/ | Confirm status with client; deploy badge if certified | Owner-side (Owner Ask #3) | Status documented; badge deployed if certified | Surfpoint has CARF Center of Excellence — Conifer should match if applicable | Owner Ask #3
LegitScript certification | ABSENT (no mention) | https://www.legitscript.com/certification/website-certification-status/ | Verify status via LegitScript lookup; deploy badge if certified | Owner-side (Owner Ask #3) | Status documented; badge deployed if certified | Blocks Google Ads compliance if HQDM ever wants PPC | Owner Ask #3
SAMHSA listing | Implied (OTP designation requires SAMHSA approval) — needs verification | https://findtreatment.samhsa.gov/ | Confirm listing live for all 7 GBPs; correct NAP if drift | HQDM-actionable | All 7 pins verified live + NAP-clean on SAMHSA | Tier 1 vertical citation | Off-Page/Citation-Submission-SOP
Insurance payor list (public) | ABSENT (admissions says 'Medicaid + most third-party payors') | — | Get full payor list from client; deploy as logo wall + named list on /admissions | Owner-side (Owner Ask #5) | Public payor list on /admissions with logos | Conversion-trust gap vs competitors | Owner Ask #5
Shatterproof ATLAS measurement program | PRESENT (about-us mention) | https://atlas.shatterproof.org/ | Add badge link to footer + admissions | HQDM-actionable | Badge + link deployed | Quality measurement membership | On-Page/Trust-Signal-Deployment-SOP
ATPA (Addiction Treatment Providers Association) | PRESENT (claimed) | — | Verify active membership; add badge to about/footer | HQDM-actionable + verify | Verified + badge deployed | Industry membership | On-Page/Trust-Signal-Deployment-SOP
NY Combat Heroin initiative | PRESENT (claimed) | — | Verify still active; add to about-us | HQDM-actionable + verify | Verified + section live on about-us | State-level initiative | On-Page/Trust-Signal-Deployment-SOP