## Pages Plan
ID | Month | Page type | Page / target | Action | Rationale axis | Why this ships now | Acceptance | Owner | Sub-brief
M1-P1 | M1 | Update | / | Deploy homepage CRD + 9 beyond-CRD additions (24 items) | REVENUE-SURFACE FIX | CRD drafted March 2026, sat unused for ~60 days. Homepage = #1 landing page (49.6% of sessions per GA4 90d). Currently OASAS/CARF/MAT/Coney Island/dual diagnosis aren't surfaced anywhere visible. Schema upgrade alone makes the page rich-result eligible for FAQ + Review + AggregateRating snippets — three SERP visibility wins from one change. Every day not shipped is high-intent traffic landing on a homepage where the credibility narrative is invisible. | All 24 items checked. Schema validator pass. Mobile + desktop verified. Every CTA routes to tel:+16463471893. GSC URL inspection submitted post-deploy. | Aleksa + Content + Dev | Surfpoint_Homepage_Update_Brief.md
M1-P2 | M1 | Update | /treatments | Hub upgrade — 15 of 16 items (T-16 rolling) | REVENUE-SURFACE FIX | /treatments ranks position 2.11 with 985 impressions / 2 clicks / 0.2% CTR in 30d. Already wins the ranking — loses the click. Title is highest-leverage CTR lever (current 32-char generic). Critical dependency: homepage H-23 internal-link contract requires /treatments H2 anchor IDs (T-05). Without anchor IDs, every contextual link added to homepage breaks. Must ship within 24h of homepage. | All 15 non-rolling items shipped. H2 anchor IDs live (required for homepage link contract). Schema validator pass. 30-day post-deploy CTR ≥ 1% (current 0.2%). | Aleksa + Content + Dev | Surfpoint_Treatments_Hub_Update_Brief.md
M1-P3 | M1 | New build | /treatments/alcohol-detox | Build Wave 1 sub-page #1 (1,400-1,600 words, universal template) | REVENUE-SURFACE FIX + GAP CAPTURE | Largest aligned cluster: 4,583 addressable monthly searches. Surfpoint already wins map pack at rank 1.47 / 96% top-3 coverage on 'alcohol rehab brooklyn'. Map visitors who don't call from GBP click to find a page that backs up the listing — and that page doesn't exist. Highest-ROI map → on-page conversion vector. Wave 1 because largest cluster + winnable despite KD 41.5 (Surfpoint's GBP + OASAS + CARF + 120-review structural advantages outweigh competitor link equity for local-pack-tied SERPs). | Universal template sections deployed. Schema validator + Rich Results Test pass. 1,400-1,600 words. Form integrated. Named MAT/MD clinician in Clinical Team section. | Aleksa + Content | Surfpoint_Treatments_SubPages_BuildPlan.md §4.1
M1-P4 | M1 | New build | /treatments/dual-diagnosis | Build Wave 1 sub-page #2 (1,300-1,500 words) | GAP CAPTURE | Leverage score 190 (KD 2.9 effective, smallest competition in entire keyword universe). Three reasons it's Wave 1 despite small volume: (1) LLM citation gap — Surfpoint cites in only 3/18 dual-diagnosis LLM prompts; this page unlocks LLM surface; (2) Differentiator vs Genesis/ACI/TBH (none offer integrated dual diagnosis); (3) No orphan to redirect from — new URL, no legacy traffic to capture, no legacy URL to retire = lowest implementation risk. | Universal template sections deployed. Schema validator pass. 1,300-1,500 words. Clinical depth section CBT-grounded. KD 2.9 — should rank top-10 within 60-90 days. | Aleksa + Content | Surfpoint_Treatments_SubPages_BuildPlan.md §4.2
M1-P5 | M1 | Fix | /about, /contact, /contact-us.com | Fix 3 broken 404s on revenue-surface URLs | STRUCTURAL FIX | Revenue-surface URLs that visitors hit directly (typed, bookmarked, backlinked) receive an error page. A 404 on a revenue-surface URL terminates conversion before it begins, on three of the highest-intent URL patterns the site has. Trivial dev effort, zero content dependency, cost of leaving them broken accumulates daily. | All 3 return 200 or 301 per crawl. GSC URL inspection clean. Internal link audit finds no remaining references to 404 variants. | Aleksa + Dev | Q2 strategy §3.5
M1-P6 | M1 | Update | 23 KEEP pages (batch) | Title + meta rewrite for 23 ranking-but-not-clicking pages | REVENUE-SURFACE FIX | 23 pages with avg position ≤ 15 on queries with ≥1,000 impressions. Anchor query: 'recovery center brooklyn' — 10,512 impressions / 0 clicks at pos 3.71. Pages already win the ranking — title/meta is the only lever to convert ranking into clicks. Low effort per page (~10 min). Batched in M1 so 30-day GSC measurement window opens before M2. | All 23 titles + metas deployed. GSC monitored 30d for CTR uplift on anchor query batch. | Aleksa | Q2 strategy §3.5 + CTR-optimization SOP
M2-P1 | M2 | New build | /treatments/opioid-detox | Build Wave 2 sub-page #3 — dual cluster (1,500-1,800 words) | GAP CAPTURE | Leverage 218 (KD 16 opioid cluster, KD 3.3 effective geo-only on MAT cluster). MAT cluster STRUCTURALLY UNDERCLAIMED by inpatient providers — top 3 on clean MAT query are Mount Sinai, Seek Counseling, One Brooklyn Health, ALL outpatient. Surfpoint is the only inpatient option mentioning MAT meds (buprenorphine, naltrexone). No inpatient provider currently ranks on 'medication assisted treatment brooklyn' because none have a dedicated MAT page. M2 because requires named MAT-supervising physician from Surfpoint Ops (unrealistic by M1 Week 1). | Universal template deployed. Two-cluster parallel H2 structure. Schema includes both MedicalProcedure entities. Named MAT-supervising clinician with credentials. 1,500-1,800 words. | Aleksa + Content + Surfpoint Ops | Surfpoint_Treatments_SubPages_BuildPlan.md §4.3
M2-P2 | M2 | New build | /treatments/short-term-rehab | Build Wave 2 sub-page #4 (1,300-1,500 words) | GAP CAPTURE | Lowest competition in entire SERP universe — only Urban Recovery (HQDM sister account) ranks in top 12 among real service providers on anchor query 'short term inpatient brooklyn'. Cluster small (~180 addressable) but SERP uncontested. Serves as the demonstrable-cadence win — a top-10 ranking within 60d would validate the universal template + sub-page strategy. M2 because pairs efficiently with opioid-detox (template work) and was deferred from Wave 1 by leverage scoring (small volume vs alcohol + dual diagnosis). | Universal template deployed. Schema validator pass. 1,300-1,500 words. 60-day post-launch GSC check shows top-15 ranking on anchor query. | Aleksa + Content | Surfpoint_Treatments_SubPages_BuildPlan.md §4.4
M2-P3 | M2 | Update | /admissions | Rebuild — consolidated form + insurance + intake clarity + schema | REVENUE-SURFACE FIX | Bottom-of-funnel page — visitors who reach it have decided on Surfpoint and are converting. Currently thin, no integrated form, no insurance section, no intake-process clarity — three of the four highest-anxiety questions for inpatient prospect. Receives meaningful GA4 traffic but converts at near-zero. M2 because rebuild reuses content patterns established on service sub-pages (Insurance We Accept, Form integration, Clinical clarity). Building in M1 would mean re-doing patterns; M2 means template already validated. | All 5 H2 sections live. Form integrated routing to intake. Schema validator pass. GSC URL inspection submitted. 30-day post-deploy conversion rate vs baseline. | Aleksa + Content + Surfpoint Ops | New brief to be authored early M2
M2-P4 | M2 | Update | /about-us | Expand with named clinical team + facility photos + accreditation badges + Person schema | REVENUE-SURFACE FIX | Most-visited non-conversion page after homepage and /treatments. Visitors hit it during consideration phase to verify legitimacy. Currently lacks named clinicians — single highest E-E-A-T signal for YMYL medical-services site and the signal that distinguishes a real treatment center from a lead-gen directory. Person schema entities created here become reusable on every service sub-page Clinical Team block. Depends on same clinical roster from Surfpoint Ops that powers homepage H-17. | Named clinical team with credentials live. Facility tour photos uploaded (5-10). Accreditation badges rendered. Schema includes AboutPage + Person entities. Rich Results Test pass. | Aleksa + Content + Surfpoint Ops | New brief to be authored early M2
M2-P5 | M2 | Update | /faq | Sync FAQ content from homepage + sub-pages into canonical destination + FAQPage @id structure | STRUCTURAL FIX | By end of M2 there will be 6 pages with FAQ blocks (homepage + /treatments + 4 sub-pages). Google deduplicates FAQ rich results across a site — only one URL gets the rich snippet per query, and Google picks. Consolidating to canonical /faq with cross-references makes the canonical choice explicit. Also serves as long-tail capture for informational queries that shouldn't host on revenue-surface pages. | Canonical /faq page with consolidated content. FAQPage schema with @id structure. All 6 source pages reference canonical entity. Rich Results Test pass on canonical URL. | Aleksa + Content | Q2 strategy §M2-09
M2-P6 | M2 | Update | Retained location pages (×10+) | Add 'Services Available in [Neighborhood]' block + per-location quality pass | STRUCTURAL FIX | Interlinking SOP gives services 15 link-plan rows vs 305 for locations and 423 for blog. Service pages = revenue surface but get zero contextual inbound. M2 work on locations × services matrix routes equity from location pages (already have inbound from blog farm + doorway redirects) toward new sub-pages that need ranking signal. M2 because requires Wave 1 + 2 sub-pages live before cross-link contracts can resolve. | 'Services Available in [Neighborhood]' block live on every retained location page. Per-location quality pass documented per page. Internal-link count to each service sub-page measured post-deploy. | Aleksa + Content | Q2 strategy §M2-09
M3-P1 | M3 | New build | /treatments/drug-detox | Build Wave 3 sub-page #5 — hub parent (1,400-1,600 words) | GAP CAPTURE | Biggest cluster (6,130 addressable monthly) but hardest competition (KD 46.9) and most national-brand SERP presence. Build LAST because: (a) /treatments hub serves the broader 'drug detox' semantic role for M1-M2; (b) substance-specific sub-pages built earlier inbound-link to this page once it ships, giving head-start on internal authority; (c) hardest-to-win cluster gets longest pre-launch ranking signal accumulation through inbound link contracts from Wave 1 + 2. | Universal template deployed. Hub-style structure with anchor links to all 4 prior sub-pages + Wave 3 benzo. Schema validator pass. 1,400-1,600 words. | Aleksa + Content | Surfpoint_Treatments_SubPages_BuildPlan.md §4.5
M3-P2 | M3 | New build | /treatments/benzodiazepine-detox | Build Wave 3 sub-page #6 — orphan capture (1,400-1,600 words) | GAP CAPTURE | Orphan /services/benzodiazepine-detox-services receives 147 imp/30d and 1,925 imp/365d at avg pos 18-30 despite being orphaned (zero internal links). HIGHEST-IMPRESSION /services/* orphan by an order of magnitude. When sub-page ships and orphan 301s to it, redirect captures impression flow into a page with proper meta + schema + form + Clinical Team. At position 10-15 with proper meta would convert 5-10% of those impressions — step-change from orphan's near-zero CTR. Wave 3 because universal template validated on 4 prior pages + drug-detox hub already shipped (internal link backing). | Universal template deployed. Schema validator pass. 1,400-1,600 words. 301 from /services/benzodiazepine-detox-services executes within 24h of launch. 30-day post-redirect: destination inherits orphan impressions, position improves toward 10-15, CTR rises 0% → ≥2%. | Aleksa + Content + Dev | Surfpoint_Treatments_SubPages_BuildPlan.md §4.6
M3-P3 | M3 | Update | /contact-us | Consolidate /contact + /contact-us + /contact-us.com → single canonical /contact-us | STRUCTURAL FIX | Completes the bottom-of-funnel consolidation started in M1-P5. M1-P5 fixed the 404s — but real consolidation onto single canonical URL with full NAP role-labeling depends on (a) homepage H-22 phone display rule live (NAP consistent sitewide) and (b) /about-us schema entity canonical (built M2) so ContactPage parentOrganization references resolve. M3 because architectural pre-reqs from M1 + M2 required before contact-page schema is well-formed. | Single canonical /contact-us URL. All variants 301. NAP block role-labeled. ContactPage schema validator pass. Service-area map iframe live. | Aleksa + Dev | Q2 strategy §3.5 + homepage brief H-22
M3-P4a | M3 | New build | /insurance/medicaid | Build carrier landing page — Medicaid | GAP CAPTURE | Insurance-carrier-modified queries represent meaningful long-tail demand — and NO direct competitor occupies this surface with dedicated carrier pages. Surfpoint accepts Medicaid per client.json. Carrier page converts carrier-modifier intent ('does medicaid cover inpatient detox in brooklyn?') into top-of-page answer + verify-coverage CTA. M3 because reuses content blocks built in M1-M2 (Insurance We Accept logic, FAQ blocks, Service entities) — per-page effort drops to ~3-4 hours vs ~10-14 hours for clinical sub-page. | Page live with carrier-specific content + FAQ. Verify Coverage CTA routes to intake form with carrier pre-selected. Schema includes Service entities. 30-day post-deploy GSC URL inspection. | Aleksa + Content + Surfpoint Ops | New brief to be authored early M3
M3-P4b | M3 | New build | /insurance/aetna | Build carrier landing page — Aetna | GAP CAPTURE | Same uncontested carrier-query surface as Medicaid page. Aetna in Surfpoint's accepted carriers per client.json. Pattern reused from M3-P4a. | Page live with carrier-specific content + FAQ. Verify Coverage CTA routes to intake. Schema validator pass. | Aleksa + Content + Surfpoint Ops | New brief to be authored early M3
M3-P4c | M3 | New build | /insurance/cigna | Build carrier landing page — Cigna | GAP CAPTURE | Same uncontested carrier-query surface. Cigna in accepted carriers per client.json. Pattern reused. | Page live with carrier-specific content + FAQ. Verify Coverage CTA routes to intake. Schema validator pass. | Aleksa + Content + Surfpoint Ops | New brief to be authored early M3
M3-P4d | M3 | New build | /insurance/bluecross-blueshield | Build carrier landing page — BlueCross BlueShield | GAP CAPTURE | Same uncontested carrier-query surface. BCBS in accepted carriers per client.json. Pattern reused. | Page live with carrier-specific content + FAQ. Verify Coverage CTA routes to intake. Schema validator pass. | Aleksa + Content + Surfpoint Ops | New brief to be authored early M3
M3-P5 | M3 | Update | /areas-served | Rebuild — real-catchment neighborhoods + service-area map + locations × services matrix | STRUCTURAL FIX | /areas-served = destination for 36 inbound 301s from Pillar 2 (27 NJ + 9 out-of-borough doorway redirects in M1). If left broken, redirects funnel into dead destination. M3 because by then all 6 sub-pages live — locations × services matrix can resolve fully (every location-page link out to every service sub-page resolves to real page). Building in M1 would mean partial matrix needing revision M2 + M3. | Real-catchment-only neighborhoods listed. Service-area map iframe live. Matrix to all 6 sub-pages. CollectionPage + ItemList schema validator pass. 36 inbound 301s validated as resolving to populated content. | Aleksa + Content | Q2 strategy §M2-09 (Pillar 2 cross-reference)
M3-P6 | M3 | Update | All KEEP pages (quarterly review) | Quarterly content review + NOINDEX re-bucketing audit-back | STRUCTURAL FIX | Pillar 2 NOINDEXes 121 URLs in M1 and DELETEs ~99 in M2. Some NOINDEX URLs may regain ranking value as broader site authority shifts during Q2. Quarterly review re-evaluates with 30-90 days of post-action data — protects against framework over-pruning. M3 because needs ~60-90 days of post-NOINDEX data to be meaningful. | Per-URL re-bucketing decisions documented. Q3 strategy framework references the decisions. Content review log appended to decision matrix. | Aleksa + Content + Aleksandar (cosign) | Q2 strategy §M3-04

## By Month
Month | Date window | # items | Headline outcome | Items
M1 | May 12 - Jun 8 2026 | 6 | Stop the bleeding + ship what's drafted. Homepage CRD + /treatments hub + 2 Wave 1 sub-pages + 3 broken 404s fixed + 23 KEEP title/meta. 4-page conversion surface vs current 1. | M1-P1 · Deploy homepage CRD + 9 beyond-CRD additions (24 items) M1-P2 · Hub upgrade — 15 of 16 items (T-16 rolling) M1-P3 · Build Wave 1 sub-page #1 (1,400-1,600 words, universal template) M1-P4 · Build Wave 1 sub-page #2 (1,300-1,500 words) M1-P5 · Fix 3 broken 404s on revenue-surface URLs M1-P6 · Title + meta rewrite for 23 ranking-but-not-clicking pages
M2 | Jun 9 - Jul 6 2026 | 6 | Service-page depth + trust-page rebuild. 2 Wave 2 sub-pages + /admissions + /about-us + /faq + service-area enhancement. 6-page conversion surface. | M2-P1 · Build Wave 2 sub-page #3 — dual cluster (1,500-1,800 words) M2-P2 · Build Wave 2 sub-page #4 (1,300-1,500 words) M2-P3 · Rebuild — consolidated form + insurance + intake clarity + schema M2-P4 · Expand with named clinical team + facility photos + accreditation badges + Person schema M2-P5 · Sync FAQ content from homepage + sub-pages into canonical destination + FAQPage @id structure M2-P6 · Add 'Services Available in [Neighborhood]' block + per-location quality pass
M3 | Jul 7 - Aug 3 2026 | 9 | Hub completion + redirect capture + carrier landing pages. 2 Wave 3 sub-pages + /contact-us + 4 /insurance/* + /areas-served + quarterly review. 14-page conversion surface. | M3-P1 · Build Wave 3 sub-page #5 — hub parent (1,400-1,600 words) M3-P2 · Build Wave 3 sub-page #6 — orphan capture (1,400-1,600 words) M3-P3 · Consolidate /contact + /contact-us + /contact-us.com → single canonical /contact-us M3-P4a · Build carrier landing page — Medicaid M3-P4b · Build carrier landing page — Aetna M3-P4c · Build carrier landing page — Cigna M3-P4d · Build carrier landing page — BlueCross BlueShield M3-P5 · Rebuild — real-catchment neighborhoods + service-area map + locations × services matrix M3-P6 · Quarterly content review + NOINDEX re-bucketing audit-back

## By Page Type
Page type | Count | Pages
New build | 10 | M1-P3 · /treatments/alcohol-detox — Build Wave 1 sub-page #1 (1,400-1,600 words, universal template) M1-P4 · /treatments/dual-diagnosis — Build Wave 1 sub-page #2 (1,300-1,500 words) M2-P1 · /treatments/opioid-detox — Build Wave 2 sub-page #3 — dual cluster (1,500-1,800 words) M2-P2 · /treatments/short-term-rehab — Build Wave 2 sub-page #4 (1,300-1,500 words) M3-P1 · /treatments/drug-detox — Build Wave 3 sub-page #5 — hub parent (1,400-1,600 words) M3-P2 · /treatments/benzodiazepine-detox — Build Wave 3 sub-page #6 — orphan capture (1,400-1,600 words) M3-P4a · /insurance/medicaid — Build carrier landing page — Medicaid M3-P4b · /insurance/aetna — Build carrier landing page — Aetna M3-P4c · /insurance/cigna — Build carrier landing page — Cigna M3-P4d · /insurance/bluecross-blueshield — Build carrier landing page — BlueCross BlueShield
Update | 10 | M1-P1 · / — Deploy homepage CRD + 9 beyond-CRD additions (24 items) M1-P2 · /treatments — Hub upgrade — 15 of 16 items (T-16 rolling) M1-P6 · 23 KEEP pages (batch) — Title + meta rewrite for 23 ranking-but-not-clicking pages M2-P3 · /admissions — Rebuild — consolidated form + insurance + intake clarity + schema M2-P4 · /about-us — Expand with named clinical team + facility photos + accreditation badges + Person schema M2-P5 · /faq — Sync FAQ content from homepage + sub-pages into canonical destination + FAQPage @id structure M2-P6 · Retained location pages (×10+) — Add 'Services Available in [Neighborhood]' block + per-location quality pass M3-P3 · /contact-us — Consolidate /contact + /contact-us + /contact-us.com → single canonical /contact-us M3-P5 · /areas-served — Rebuild — real-catchment neighborhoods + service-area map + locations × services matrix M3-P6 · All KEEP pages (quarterly review) — Quarterly content review + NOINDEX re-bucketing audit-back
Fix | 1 | M1-P5 · /about, /contact, /contact-us.com — Fix 3 broken 404s on revenue-surface URLs

## Dependencies
Predecessor | Relationship | Successor | Why
M1-P1 (Homepage CRD H-23 links) | blocked by | M1-P2 T-05 (anchor IDs on /treatments) | Homepage H-23 contextual links target /treatments#alcohol-detox etc. — must ship within 24h of each other or homepage links break
M1-P3 + M1-P4 (Wave 1 sub-pages) | blocks | Pillar 2 S1-07 (Wave 1 /services/* 301s) | 301 redirect needs a destination page; ships AFTER sub-pages
M2-P1 + M2-P2 (Wave 2 sub-pages) | blocks | Pillar 2 S2-03/04 (Wave 2 /services/* 301s) | Same redirect destination pattern
M3-P1 + M3-P2 (Wave 3 sub-pages) | blocks | Pillar 2 S3-02/03 (Wave 3 /services/* 301s) | Same pattern — benzo redirect captures highest-impression orphan flow (1,925 imp/365d)
M1-P1 H-17 (homepage clinical team) | blocks | M2-P4 (/about-us Person entities) | Named clinicians from homepage become canonical Person entities on /about-us — roster validated on homepage first
M2-P4 Person entities | blocks | Every M1-M3 service sub-page Clinical Team block | Person schema canonical entity lives on /about-us; service pages reference via @id
Surfpoint Ops clinical roster delivery | blocks | ~7 M1-M3 pages with Clinical Team section | Single highest-risk dependency in the plan — gates homepage H-17, /about-us, every service sub-page
M1-P1 H-22 (phone display rule) | blocks | M3-P3 (/contact-us consolidation) | ContactPage NAP block must match sitewide phone display rule
M2-P4 (/about-us canonical) | blocks | M3-P3 (/contact-us ContactPage references) | ContactPage parentOrganization references /about-us schema entity
Pillar 2 M1 doorway redirects | blocks | M3-P5 (/areas-served rebuild value) | /areas-served is the destination for 36 inbound 301s — rebuild lands when matrix is complete
M1-M3 sub-pages live (cumulative) | blocks | M3-P5 (locations × services matrix) | Matrix can resolve fully only when all 6 sub-pages live

## Success Metrics
Metric | Current (2026-05-12) | M3 target | Read
Service-page sessions (5 sub-pages + homepage + /treatments combined, 90d) | 104 | 600+ | 6x funnel-surface expansion
Service-page conversions (direct attribution, 90d) | 0 | 8-15 | Inverts the 0-conversion problem
Service-page top-10 ranking on anchor queries | 0 / 6 | 4 / 6 | Wave 1 + Wave 2 leverage scores
Homepage avg position on 'drug rehab brooklyn' cluster | 5.8 | 3.0 | CRD + schema + internal-link contracts
/treatments hub CTR | 0.2% | >=1.5% | Title + meta rewrite + content depth
Rich-result eligibility (FAQ, Review, AggregateRating) | 0 types | 3 types active | Schema deployment across all KEEP pages
Indexed pages from /treatments/* | 0 | 6 | All 6 sub-pages indexed post-M3
404 / broken revenue-surface URLs | 3 | 0 | Structural fix
Pages with FAQPage schema | 0 | 6+ | Canonical at /faq, references on each sub-page
Person schema entities | 0 | 1 per named clinician | Canonical at /about-us