Push 1 Brief — GBP Depth Surge (Defend Red Hook + Diffuse)

| Client: Urban Recovery (Red Hook Brooklyn) | Quarter: Q2 2026 | Prepared: 2026-05-18 |
| --- | --- | --- |

Problem statement

Urban Recovery's GBP is the moat — the pin holds 92.8% of the 13×13 grid and the GBP-tagged homepage path (/?utm_source=gmb) drove 3,275 clicks / 365d at 1.18% CTR (the highest non-blog converting URL on the site). But the pin's depth signal is dramatically under-indexed vs the competitive set.

| Signal | Urban Recovery | Competitor benchmark |
| --- | --- | --- |
| Total photos | 7 | Ascendant 90 / Mountainside 30 / ACI Inpatient 12 |
| GBP Posts in scrape window | 1 | Direct competitor Detox & Drug/Alcohol Rehab Center NY: visible weekly cadence |
| Reviews | 111 | Surfpoint sister pin: 4.8★ × 94 (4.8 vs UR 3.8) |
| 1-star share | 23% (26 of 111) | Healthy NYC pins: <10–15% |
| place_topics | null | Detox & Drug/Alcohol Rehab Center NY: populated |
| Owner replies on <4★ reviews | 0 of 30 | NYS Detox / Ascendant: visible owner-reply velocity |

Why this matters: Photos count is a documented E-E-A-T trust signal + Maps freshness ranker. Posts cadence is a Maps freshness signal — Detox & Drug/Alcohol Rehab Center NY (UR's direct competitor at +52 cells) has visible cadence. The 23% 1-star share is a documented YMYL Maps deprioritization signal. place_topics = null means Google hasn't yet derived enough review-content density to assign topical tags.

Why Push 1 first: UR's grid hold is real but defensible only if depth signals reach competitive parity. The pin is gaining ground passively (+21 top-10 cells) while the field churns hard around it — push the depth signals and that gain accelerates.

____________________________________________________________

Section 1 — GBP Posts cadence M1-M3 (GBP-01 / GBP-05 / GBP-06)

Target: 4 Posts/month sustained M1-M3 (= 12 total Q2). Each Post links to a relevant on-site URL per Urban_Recovery_Internal_Linking_Map.csv rows IL-60 / IL-61 / IL-62. Image per Post geotagged to 40.6754,-74.0148.

Topic mix per month:

1 owned-query topic (alcohol/drug rehab brooklyn)

1 climbing-query topic (Medicaid acceptance / same-day admissions / medical detox)

1 Inpatient-framing topic — explicit "Inpatient Drug & Alcohol Rehab Brooklyn" phrasing (counters SNF category drift on inpatient rehab query; Brooklyn Center for Rehabilitation and Nursing entered 0→102 cells)

1 differentiator topic (LGBTQ+-affirming / women-owned / transgender-safespace)

M1 specific Posts (per `OffPage_Stack_Template.csv` GBP_Posts tab filter month=M1):

"Alcohol & drug rehab in Red Hook — what makes Urban Recovery different" → /services/alcohol-detoxification-service

"Medicaid acceptance for detox at Urban Recovery" → /insurance

"Inpatient drug & alcohol rehab Brooklyn — 24-hour medical supervision" → /services/short-term-residential-program

"LGBTQ+-affirming inpatient rehab in Red Hook" → /about-us

M2 Posts route to upgraded SP-01 alcohol-detox + LP-02_M1 anchors (Red Hook + Carroll Gardens + Gowanus).

M3 Posts route to upgraded SP-02 opioid-detox + MAT + LP-02_M2/M3 cross-borough URLs + 3 Q-format CON-03 articles.

Acceptance:

4 Posts/month shipped; screenshot evidence filed

1 Inpatient-framing Post per month minimum

Topic mix tied to monthly publish calendar

____________________________________________________________

Section 2 — Review velocity push (GBP-03)

Target: +20 reviews/month M1-M3 → 111 → 170+ by M3 close. 1-star share 23% → <18% via positive-volume dilution.

Mechanism: Surfpoint sister pin reached 4.8★ × 94 reviews via HQDM Review-Velocity-SOP. Same SOP applies here. Intake team owns the operational layer:

Post-discharge prompt at 7-day mark with link to GBP review URL

Signed-release follow-up at 14-day mark for non-responders

Prompt language biased toward specific service-experience phrasing (per Push 5 LLM-citation strategy — same prompt template feeds both review topic-density and citation surface)

Owner-side actions (no new asks):

Owner provides signed releases for review-followup workflow

Owner confirms post-discharge contact protocol with intake team

Acceptance:

+20 reviews logged M1 per Reporting Master

Sustained M2-M3 → 170+ by M3 close

1-star share trajectory tracked weekly

Reporting team logs weekly count delta in REP-01

____________________________________________________________

Section 3 — Photo blitz 7 → 30+ (GBP-04, M2)

Owner-gated. HQDM delivers the photo brief; owner uploads.

6 photo categories, 30+ total:

Exterior 411 Van Brunt St (4-6 photos) — building entrance + signage + Red Hook waterfront context + IKEA-direction reference

Interior treatment rooms (6-8 photos) — patient rooms (no PHI), common area, group therapy room, individual session room

Intake desk + lobby (3-5 photos) — first-touch consumer experience

Staff (3-5 photos) — HIPAA-conscious framing (signed releases on file); clinical lead + intake coordinator + medical director if available

Red Hook neighborhood (3-5 photos) — waterfront, neighborhood landmarks, transit access from Carroll Gardens / Gowanus / Sunset Park

Women-owned + LGBTQ+ environmental cues (3-5 photos) — pride flag display, women-led leadership wall, transgender-safespace signage

Composition guidelines:

Landscape orientation primary (Maps prefers)

1200×900 px minimum

Natural lighting where possible

All photos geotagged to 40.6754,-74.0148 via EXIF

No PHI / no patient faces / no patient-identifying details

HQDM deliverable: Photo brief PDF + photo upload SOP. Drive-shared with owner via AM.

Acceptance:

30+ photos uploaded across 6 categories

Verify via DataForSEO Business Data scrape post-deploy

Logged in Urban_Recovery_GBP_Action_List.csv row GBP-04 with upload date

____________________________________________________________

Section 4 — Services + attributes + description tightening (GBP-02 / GBP-05 / GBP-06 / GBP-08)

GBP Services tab audit (GBP-02, M1):

Confirm 5 existing services listed (Alcohol Detox + Drug Detox + Opioid Detox + Benzo Detox + Short-Term Residential)

Add 100-200 character custom descriptions per Service

Conditional: Add 5 MAT-specific Services (MAT / Methadone / Suboxone / Vivitrol / Buprenorphine) if confirmed in Owner Items #1

GBP attributes (GBP-05, M1):

Confirm 4 differentiator attributes visible: is_owned_by_women, welcomes_lgbtq, is_transgender_safespace, has_wheelchair_accessible_entrance

Populate empty subsections: Amenities + Crowd + Service options + Languages + Place-page attributes

GBP description tightening (GBP-06, M1):

Add OASAS license number (Owner Items #1)

Add "same-day admissions" explicit phrase

Add borough-access phrase: "serving Red Hook, Carroll Gardens, Park Slope, Sunset Park, Downtown Brooklyn"

GBP categories audit (GBP-08, M1):

Confirm primary = "Addiction treatment center"

Confirm 4 secondary categories load in Map Pack filter chips

Consider adding "Detox center" as secondary if available

____________________________________________________________

Section 5 — Owner replies on <4★ reviews (GBP-07, M3)

Target: Owner reply on all 30 <4★ reviews (26 1-star + 4 2-star) by M3 close.

Mechanism: Owner-replies reduce topic density of negative content in GBP review embeddings (place_topics derivation). Per feedback_hqdm_drop_gbp_qa.md — no Q&A work this quarter (Google AI-answer migration); reviews are still owned by listing managers.

Reply template (HQDM Owner-Reply-SOP):

Empathetic acknowledgment of patient experience

Outcome statement (what UR has done since / what UR offers)

No PHI / no patient-identifying detail

No legal-defense framing

Sign-off from clinical lead or AM with named role

Owner-side: AM coordinates the reply sweep with the owner; HQDM verifies count post-deploy via DataForSEO Business Data scrape.

Acceptance:

Every <4★ review has an owner reply by M3 W4

M3 +20 reviews logged

1-star share <18% measured at M3 close

____________________________________________________________

Aggregate acceptance criteria

Posts: 12 Posts published across Q2 (4/month sustained)

Photos: 7 → 30+ (M2)

Reviews: 111 → 170+ (M3)

1-star share: 23% → <18% (M3)

Owner replies: 0 → 30/30 on <4★ reviews (M3)

Services + attributes + description: all GBP-02/05/06/08 actions deployed M1

All Posts geotagged 40.6754,-74.0148 with on-site link per IL-60/61/62

Non-asks

No Q&A work — Google migrated GBP Q&A to AI-generated answers; not a managed surface anymore per feedback_hqdm_drop_gbp_qa.md

No competitor-pin attack / GMB takedown work — Tier 0 scope; standard Push 1 skips this entirely per feedback_hqdm_no_gbp_takedown_scans.md

No new pin creation within the primary client account this quarter (GBP-04 is enrichment of existing pin)