## Schema Deployment (M1-M3)
Month | URL | Schema type | Action | Validator | Notes | Owner
M1 | / | LocalBusiness | Fix telephone field — (646) 960-6656 → (646) 347-1892 (GBP canonical) | Rich Results Test | HP-01 NAP fix; one-line edit | Aleksa
M2 | /services/alcohol-detoxification-service | Service + LocalBusiness + FAQPage | Deploy as part of SP-01 universal-template upgrade | Rich Results Test | SP-01 task | Aleksa + Content
M3 | /services/opioid-detoxification-services | Service + LocalBusiness + FAQPage | Deploy as part of SP-02 universal-template upgrade | Rich Results Test | SP-02 task | Aleksa + Content
M3 | /blog/* (top on-topic refreshed via CON-05/06/07) | BlogPosting + FAQPage | Deploy on each refreshed blog post that lacks schema | Rich Results Test | Paired with HQDM Blog-Refresh-SOP | Aleksa
M3 | /faq + service-page FAQ sections | FAQPage | Audit + extend | Rich Results Test | ON-07 audit | Aleksa
M3 | sitewide | BreadcrumbList | Audit + close gaps | Rich Results Test | ON-07 audit | Aleksa
— | /locations/* (Brooklyn anchor builds) | LocalBusiness + BreadcrumbList | See LP-02_Builds_Schema tab of Urban_Recovery_Location_Pages_Plan_3Month.xlsx | Rich Results Test | Schema for new location builds is merged with the build task (LP-02); not duplicated here | Aleksa + Dev

## ON-07 Validation Pass (M3)
Month | URL or pattern | Schema type to validate | Acceptance bar | Result | Notes
M3 | Homepage | LocalBusiness | RRT pass + NAP matches GBP canonical |  | Verifies HP-01 stuck
M3 | 6 BUILD location URLs (LP-02_M1 + LP-02_M2) | LocalBusiness + BreadcrumbList | RRT pass + breadcrumb chain |  | Verifies LP-02 builds stuck
M3 | /services/alcohol-detoxification-service | Service + LocalBusiness + FAQPage | RRT pass on all three |  | Verifies SP-01
M3 | /services/opioid-detoxification-services | Service + LocalBusiness + FAQPage | RRT pass on all three |  | Verifies SP-02
M3 | Other /services/* (3 remaining) | Service | RRT pass — minimum schema |  | Q3 upgrade candidates
M3 | Refreshed /blog/* posts (CON-05/06/07) | BlogPosting + FAQPage | RRT pass per post |  | Schema added during refresh
M3 | sitewide BreadcrumbList | BreadcrumbList | Coverage report |  | Audit completeness